## Sheet1
A | B | C | C
Task | Start (week) | Duration (week) | Type | (SW)/Hardware Requirement (HW)/Derived Requirement (DR)/Nice to have Requirement (NTH)/Software Constraint(SWC)
Cross-Site Request Forgery protecction (Mengyuan Zhu) | 0 | 2 | SW
User password bcrypt/scrypt (Mengyuan Zhu) | 2 | 2 | SW
SSL/HTTPs for sensitive pages (Mengyuan Zhu) | 3 | 2 | SW
favicon.ico (Mengyuan Zhu) | 4 | 1 | SW
Payment/Stripe (Mengyuan Zhu) | 5 | 3 | NTH
sitemap.xml (Mengyuan Zhu) | 6 | 2 | SW
gzip/deflate on pages (Mengyuan Zhu) | 7 | 2 | SW
Pagespeed/insight optimization (Mengyuan Zhu) | 8 | 2 | SW
Mobile optimization (Mengyuan Zhu) | 9 | 2 | SW
User history analytics (Mengyuan Zhu) | 10 | 2 | SW